Planning Manual for Summer Conferences

Part 1: General Chair

Part 2: Technical Chair

Version 1.0 - August 2000

Part 1

Manual for General Chairs of the Summer Conference

This manual should also work well for planning for Winter Conferences with appropriate changes in dates and schedules.

Manual for General Chairs of the Summer Conference

General Comments

The following manual is written with the summer conference used as an example.  The appendices are also for the summer conference.  However this manual can also be used for the winter conference with obvious changes.  Since there are fewer registrants for the winter conference, this must be taken into account when figuring the budget as in Attachment 2.  The schedule shown in Attachment 3 must also be adjusted for the difference in dates.

Hotel Site

Once the general area for the conference is decided, a letter should be sent to the hotels and other facilities in the area.  A letter should also be sent to the local visitor’s and convention bureau and the chamber of commerce.  This letter should clearly identify the conference along with the number of people expected and what kind of facilities and activities are needed.  A sample letter (used for the Alaska Conference) appears in Attachment 1.

Several proposals from hotels or other facilities at the site should be obtained.  These proposals should include at least the following:

Room rates and number of rooms to be guaranteed/cutoff date of available rooms

Rental for facilities

Rental for a/v equipment

Number and size of room for meetings and number of people that can be held theater style   Setup fees for the rooms

Registration area

Paper sales room

Breakfast setup for speakers’ breakfast

If the reception and dinner is to be held at the same site then the following must also be included:

A list of types of food available and the costs

Number of people that the rooms can hold for the type of affair planned and setup fees

Additionally, any activities in the area should also be listed(along with costs(such as:

Hiking trails

Golf

Tours

Etc.

Once a specific proposal is agreed upon, the negotiations with the hotel should include, if possible, a guaranteed price for all rooms and food for the date of the meeting.  Some hotels will do this up to two years in advance and others will simply give the current costs and estimate a percentage increase for the time of the conference.  If the latter is done, then a guarantee of a maximum increase should be obtained.  This makes it easier to do an accurate budget.  If no guarantee is given, another site should be chosen.

As stated above there should be a fixed number of rooms guaranteed.  If possible, it is best to have the date of this commitment on the number of rooms no earlier than several weeks after the Abstract due date.  Allow for the usual one-month abstract date extension. This will allow for a better estimate of the number of attendees as determined by the abstracts submitted and can help in determining overall costs.

If all costs can be defined and guaranteed at the time of signing the contact then this is the best since it allows almost all items to be listed in the preliminary budget and an accurate cost for almost the entire conference can be obtained.

The AAS representative, Carolyn Brown, and not the general chairs should sign the contract.  The contract should also state who is responsible for authorizing additional costs such as additional a/v or room rental, or additional food.  Usually these are the two general chairs.  The contract should also clearly state the number of guaranteed sleeping rooms, the meeting rooms, the food service and all other service provided. Some hotels offer free sleeping rooms for every x number of sleeping rooms filled.  This should be clearly stated in the contract.

# Registration and Attendance at Food Affairs

The amount to be charged for registration is the most difficult item to be determined.  The web site offers historical data on attendance by number of members (of AAS or AIAA), nonmembers, and students.  Each are charged a different fee.  Typically 200 registrants (for the summer conference) is a good number to work with but this has varied widely.  The web site should be used to determine this number.  The registration fee can then be determined based on the costs as projected in the budget.

The attendance at the various functions is also difficult to determine.  The early bird reception held on the evening of the first registration will have a lower attendance than the second reception.  There is no historical data for this or for the second reception.  But since the receptions are open to registrants and their families, this additional number must be taken into account.  The chairmen should settle on a number that is guaranteed to the hotel and this is the number that the food is determined from.  This represents the basis for the cost of the reception and is the basis for the cost in the budget.  If the hotel has a good staff for the banquets, they can recommend food that can be increased beyond the guaranteed amount which will not add seriously to the costs.  This means that a contingency may be added to the cost of the reception to allow for growth.

The banquet attendance and cost is determined by the food service and the number of people that can attend.  There is usually a maximum attendance level (due to rooms size, etc.) and since the conference must guarantee a minimum number for which the conference will be charged, this must be done with care or there can be a charge if not enough people attend.  If the cutoff number is set too small, there may be unhappy people.  A cutoff date for the guaranteed attendance near the first or second registration day would be the best for by then, it would be known how many people may attend.  However, this means that there would be no accurate estimate in the budget and this lends some unknown factors in determining the registration fee.  The conference registration fee usually includes a subsidy for the dinner.

Consideration needs to be given to the policy of students, children and other guests (not spouses or significant others) attending the banquet.  Since the banquet is usually subsidized by the registration fee, if there is limited attendance then those conference attendees who cannot go are subsidizing the attendance of outside guests and children. This can be a problem and needs to be addressed with a set policy.

Food and drink is usually the most expensive item on the budget and great care is needed here.  How the chairs handle drinks is also important.  In the past, an open bar was sometimes used but as the costs have increased this has evolved into two free drinks per person.

# Budget

A sample budget, used for the Alaska conference is included in Attachment 2.  The budget must include all known costs and a glance at Attachment 2 will show almost all of these.  These include pre-conference costs such as mailings and printings, purchase of supplies, and the cost of advertising the call for papers in the AIAA Journal.  These pre-conference costs are usually paid by the AAS and must be reimbursed.  Some hotels also charge a fee if the food service or drink service is below a certain number and this should be known in advance and included in the budget.  Contingencies for cost growth can be added to the budget in several ways.  Contingencies may be added for each item, such as banquet, reception, A/V equipment, etc.  Or one contingency may be added to the total expected budget.  For Alaska, both were done and it turned out to be too much.  If the hotel guarantees its prices, only a small contingency may be needed.  If the prices are not guaranteed in some areas, a contingency in that area is probably needed.  As seen on the sample budget, the contingency is included in determining the final registration fee.

# Schedule of Events

A calendar with a schedule for the completion of various tasks is a very helpful tool to ensure that important items are completed in the proper time frame.  A sample is in Attachment 3.  It is recommended that all chairs, technical and general, have a copy of this schedule and adhere to it as much as possible.

# Just Prior to the Conference

A bank account or checking account should be opened with a local bank.  This allows for easy payment of bills, but most importantly for the safe handling of money to be transferred back from the conference.  If this can not be done, then a bank account in the home location of one of the general chairs should be opened.  The checks acquired at the conference can then be mailed back to the account and any cash can either be used to pay bills on site or can be deposited with the hotel for them to write a check that can then be mailed back.

# At the Conference

The general chairs should handle the initial registration as problems and questions may arise that have not been previously addressed.  After that, volunteers, or preferably paid helps can handle the registration and paper sales.

As stated, only certain people should be authorized to commit new expenditures with the hotel.

A safe deposit box is a must to store daily receipts prior to deposit in the bank.

All cash should be used to pay hotel bills on site if possible.

# Recommendations and Questions to Be Decided.

How many drinks to allow to registrants and how many to accompanying person such as spouses and children?

Do students receive the same benefits (discounts on dinner tickets and drinks) as full paid registrants?

Do accompanying persons receive the same discount on dinner tickets as full paid registrants?

LIST OF ATTACHMENTS

ATTACHMENT 1:		Sample Letter to Hotels

ATTACHMENT 2:		Sample Budget

ATTACHMENT 3:		Schedule of Events

ATTACHMENT 1- Sample Letter to Hotels

The American Astronautical Society (AAS) would like to hold its annual summer meeting in August of 1999 in Anchorage, Alaska.  I am one of the two General Chairs planning this conference.

The conference typically registers 200+ participants many of whom bring their families since we like to schedule the conference in places that are good for family vacations.  The participants come from government, industry, universities, and from many countries.  Because many of our participants are from government we would like to accommodate them at government rates.

We usually have several receptions at the conference hotel site or nearby.  These receptions consists of finger food and drinks.  We also have a separate evening affair which is usually an informal dinner or cookout.  These events are attended by all registrants and their families.

The conference is run with three parallel sessions, both in the morning and afternoon, with seating in theater style for about 75 to 100 people each.  In addition we need a place to set up the registration desk and a separate room in which we will sell papers that are being presented at the conference.

During the conference days, we have a speakers breakfast each morning for approximately 50 people.  This breakfast usually consists of rolls, muffins, fruit, juice, and coffee.  During the meetings, we have two breaks, one in the morning and one in the afternoon during which coffee and soda is available.

We would normally like to block a number of rooms for our registrants at a guaranteed rate.  If a government rate is available we would like a limited number of rooms at that rate.  If the rooms can be available for 3 days before and after the conference at the conference price, that would also be good since many people like to extend their trip.

If your hotel is interested in being the site for our conference, I would appreciate a proposal from you along with information regarding the hotel.

If there are any questions, I can be reached at my office at the Naval Research Laboratory at:

email:		kaufman@ssdd.nrl.navy.mil

phone:		202-767-0513

fax:		202-404-7516

home phone:	301-449-7498

home address:	6408 Glen Oak Dr.

Temple Hills, MD 20748

We will be having our next planning meeting in February 1998 and at that time we will make our final decision on hotels and precise location.  Therefore I would like to have the information well in hand by that time.

Thank you for your prompt reply to this request.

ATTACHMENT 2 - Sample Budget

ATTACHMENT 3 - Schedule of Events

Part 2

Manual for Technical Chairs of the Summer Conference

This manual should also work well for planning for Winter Conferences with appropriate changes in dates and schedules.

Manual for Technical Chairs of the Summer Conference

Introduction

The Technical Chairs have overall responsibility for the technical content of the conference.  They determine the scope of the conference and solicit papers through the call for papers.  Based on the submitted abstracts, they assure high technical quality of the conference through their own reviews and subsequent reviews by session chairs.  They are responsible for assembling the conference program complete with all abstracts.  At the conference they ensure that session chairs are present and understand their roles.  They have responsibility for paper sales and collection of papers for the proceedings.

# Electronic Processing

Since the Sun Valley Conference in the summer of 1997, we have made increasing progress toward an all-electronic handling of the technical aspect of the conference.  The process begins with the call for papers.  Authors should be required to supply an email address for all future correspondence.  All subsequent correspondence with authors and session chairs can then occur by email.  Authors should submit both their extended abstract and 100-word abstract electronically.  This facilitates production of the program with abstracts.

# Call for Papers

The first item to be accomplished is the call for papers.  The Technical Chairs should determine the scope of the conference and decide if any special areas will be solicited.  A sample call for papers is included as Attachment 1.  The call for papers should be published in the AIAA Aerospace America magazine as well as the AAS Newsletter in the fall time period.

The number of papers received and accepted will be a major factor in determining the conference schedule.  A large response to the call may allow the conference to be extended to a fourth day.  However, a decision on the length of the conference is subject to dates set by the hotel for changes.  Thus, the deadline for abstract submittal should be early enough to allow ample time to receive all abstracts, review them, and make a final decision on conference length meeting deadlines set by the hotel.  It has been our experience that less than 50% of the abstracts will be received by the announced date.  Typically, we have extended the deadline by 2 to 4 weeks at which point most abstracts will be received.  A timeline of cumulative number of abstracts received for a conference is provided as Attachment 2.

# Session Chairs

Session Chairs should be knowledgeable and a recognized contributor in the subject matter of their session.  The primary source of Session Chairs is the membership of the AAS Spaceflight Mechanics and AIAA Astrodynamics Technical Committees.  Volunteers are solicited by passing around a sign-up sheet at the committee meetings.  A sample sign-up sheet is included in Attachment 3.  The sign-up should occur at the committee meetings of the conference prior to the one being worked.

Abstract Review and Selection

Abstracts are sent to the Technical Chairs.  It is recommended that a database be developed as the abstracts are received.  A FilemakerPro progam has been developed for this purpose but a simple spreadsheet also works very nicely.  The data collected should contain:

- Author names

- Paper title

- Corresponding author address including email

- Date received

This spreadsheet can be easily manipulated to make session assignments and sequential paper numbering for the program.  An extract from an example spreadsheet is included in Attachment 4.

The Technical Chairs perform an initial review of the papers for technical quality.  Those abstracts that are accepted by the Technical Chairs are assigned to a general topical area, and the number of papers per session is balanced.  It is at this point that the Chairs make an initial assessment of the number of sessions and the length of the conference.  Some flexibility for number of papers presented per day can be gained by the choice of length of paper presentation.  Some conferences have allowed as much as 30 minutes and some have allowed as little as 20 minutes.

After initial review and session assignment, each set of papers is sent to the session chair for a second technical review.  The session chair, being knowledgeable in the subject matter may also recommend that a paper be transferred to another session.  An example letter to session chairs in included in Attachment 5.

After the session chair reviews, the Technical Chair make the final acceptance determination and session assignments.  They then provide to the authors a letter of acceptance or rejection as appropriate.  Acceptance letters also contain explicit instructions on paper preparation and dates for further provision of information to the Chairs.  Sample acceptance and rejection letters are provided in Attachments 6 and 7, respectively.

At this point, a preliminary version of the program, less abstracts, should be posted on the AAS website.

Program

Development and production of the program is also the responsibility of the Technical Chairs.  The most difficult part of this is obtaining 100-word abstracts from every author.  It requires persistence to obtain every last abstract but the satisfaction of a complete program is worth the effort.  Email is invaluable for this task.  After the program is complete, it should be posted on the AAS website in place of the preliminary program posted previously.

Printing of the program is done in various ways.  Some chairs have taken it to a professional printer while others have been able to persuade their parent organization to donate the cost of printing.  Regardless of the source you use, allow ample time so that you can ship the programs to the conference hotel rather than transporting them yourself.

# At the Conference

The Technical Chairs have continuing responsibilities at the conference.  These include:

- Set up of Technical Paper sales area.  It is recommended that each AAS Paper number be printed in large font on a separate sheet of 8 ½ X 11 paper.  These should be laid out in order on the paper sales table prior to arrival of the first papers

- Receipt of technical papers from authors.  The authors may also provide a camera-ready copy of their paper and possibly a floppy disk.  These should be set aside for later mailing to the proceedings publisher.

- Paper Sales.  The Technical Chairs handle the sales of papers.  They provide manning themselves and also recruit others for support.  They should tally sales at the end of each day and secure the funds.  The funds can be turned over to the General Chairs for safekeeping by the hotel.

- Speakers’ Breakfast.  The Technical Chairs host a speakers’ breakfast each morning.  A number of tables should be available corresponding to the number of sessions to be held that day (usually 6).  A sign should be prominently displayed on each table so that speakers can locate their session chair.  Speakers should be reminded of the procedures and time limits for their talks.  This breakfast also affords an opportunity for session chairs to meet authors that they do not know and to obtain bios for authors who have not previously supplied them.

- Monitoring Technical Sessions.  Periodically, one of the Technical Chairs should check on the technical sessions to make sure that things are going smoothly.  Problems such as crowded rooms, inadequate heating or cooling, etc. should be quickly and aggressively pursued with the hotel.

- Mailing for Proceedings.  At the conclusion of the conference, three copies of each paper should be collected and mailed to the editor of the Proceedings along with the camera-ready copies and disks supplied by the authors.

# Schedule

A typical schedule of actions to be taken is included in Attachment 8.

LIST OF ATTACHMENTS

ATTACHMENT 1:		Conference Call for Papers

ATTACHMENT 2:		Timeline of Cumulative Number of Abstracts Received

ATTACHMENT 3:		Session Chair Volunteer Signup Sheet

ATTACHMENT 4:		Spreadsheet for Technical Program Planning

ATTACHMENT 5:		Initial Instructions to Session Chair

ATTACHMENT 6:		Author Acceptance Letter

ATTACHMENT 7:		Author Rejection Letter

ATTACHMENT 8:		Planning Schedule and Tasks

ATTACHMENT 9:		Foreign Author Letter of Invitation

ATTACHMENT 10:		Technical Paper Cover

ATTACHMENT 11:		Template to use for signs/placards on meeting rooms

ATTACHMENT 12:		Session Chair Reminder Letter

ATTACHMENT 13:		Personal Conference Planner

ATTACHMENT 1

AAS/AIAA Astrodynamics Specialist Conference

August 16-18, 1999

Westin Alyeska Prince Hotel

Girdwood, Alaska (near Anchorage)

Abstract Deadline: February 15, 1999

The 1999 Astrodynamics Conference, hosted by the American Astronautical Society (AAS) and cosponsored by the American Institute of Aeronautics and Astronautics (AIAA), will be held August 16-18, 1999 in Girdwood, Alaska, near Anchorage.  The conference is organized by the AAS Space Flight Mechanics Technical Committee and the AIAA Astrodynamics Technical Committee.

Papers are sought for all areas of astrodynamics.  Topics of interest include, but are not limited to:

- Orbital dynamics, perturbations, stability

- Trajectory design and optimization

- Navigation, guidance and control

- Attitude dynamics of rigid and flexible space structures

Papers which contain experimental results or current data are especially encouraged.

In addition, proposals are solicited for appropriate subjects for special sessions from perspective session organizers.  Areas of interest include, but are not limited to:

- Parallel processing applications in astrodynamics

- Attitude control and estimation for small satellites

- History and future of the US space program

- Panel discussions

Papers will be accepted on the basis of extended abstracts.  The extended abstract must be at least 500-1000 words and should include a description of the problem addressed and the results obtained, as well as a brief summary of the solution procedure and relevance to astrodynamics research.  Abstracts may also contain supporting figures and/or tables.  The abstract must include paper title, names and affiliations of all authors.

In addition to the extended abstract, you must include the following information to facilitate future correspondence:

- Name, affiliation, address, telephone number, fax number and email address for the corresponding author.

A “no paper-no podium” rule will be in effect for all presentations.  An author will not be permitted to give his or her paper if a written paper has not been prepared and made available at the conference.  AAS will not consider for presentation or publication any paper that has been presented or published elsewhere.  Authors will be required to sign a statement that the paper has not been previously presented or published.

Special sessions may be as long as four hours on a selected topic.  Their purpose is to invite discussion and the exchange of ideas on “hot topics” in the astrodynamics community and may take a variety of formats, e.g. panel discussions, invited speakers and/or papers, questions and answers, or interactive workshop.  Prospective special session organizers should submit a proposal consisting of a title, a brief description of the session of less than 500 words, and a list of proposed activities and/or invited speakers and titles.

The American Astronautical Society Space Flight Mechanics Technical Committee also announces the John V. Breakwell Student Travel Award. This award provides a maximum of $1000 to cover travel expenses for U.S. and Canadian students planning to attend the AAS/AIAA Astrodynamics Specialist Conference.  For further details about applications for the award as well as continually updated information concerning the conference, please see the Space Flight Mechanics website at http://www.space-flight.org.

Warning --- Technology Transfer Considerations

Prospective authors are reminded that technology transfer guidelines have substantially extended the time required for review of abstracts and completed papers by US government agencies.  Internal (company) plus external (government) review can consume 16 weeks or more.  Authors should determine the extent of approval necessary early in the paper preparation process to preclude paper withdrawals and late submissions.

Two copies of the extended abstract should be submitted to each of the Technical Chairs listed below.  The deadline for submission of the abstract is February 15, 1999.  Formal letters of acceptance with complete instructions will be sent to authors approximately April 10, 1999.

AAS Technical Chair

Kathleen Howell

School of Aeronautics and Astronautics

GRIS 1282

Purdue University

West Lafayette, IN 47907-1282

765/494-5786   765/494-0307 FAX

email: howell@ecn.purdue.edu

AIAA Technical Chair

Felix Hoots

GRC International

Suite 310

985 Space Center Drive

Colorado Springs, CO 80915

719/596-5395    719/596-6139 FAX

email: fhoots@grci.com

# AAS General Chair

Bernard Kaufman

Astro Dyn

6408 Glen Oak Dr.

Temple Hills, MD 20748

301/449-7498    301/449-2986 FAX

email: bkaufman@erols.com

# AIAA General Chair

Terry Alfriend

Aerospace Engineering Dept.

H.R. Bright Bldg., Room 701

Texas A&M University

College Station, TX 77843-3141

409/845-5920    409/845-6015 FAX

email: alfriend@aero.tamu.edu

## ATTACHMENT 2

## ATTACHMENT 3

Session Chairs

Name				Area of Interest		Address				Phone		E-mail

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

__________________	__________________	__________________________	__________	__________

ATTACHMENT 4

|  | AUGUST 1999 - AAS/AIAA ASTRODYNAMICS CONFERENCE - ALASKA |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AAS # | No. | Rec'd | Receipt E-mailed | Author | Title | Addresses | Session # |
| Sess 1 | Mission Design: Mars - Bob Melton |  |  |  |  |  |  |
| 300 | 144 | 03/02/99 | 03/03/99 | Cesarone, R.J. Hastrup, R.C. Bell, D.J. Roncoli, R.G. | Architectural Design for a Mars Communications & Navigation Orbital Infrastructure | Jet Propulsion Lab, California Institute of Technology, 4800 Oak Grove Dr, Pasadena, CA 91109, alfriend@aero.tamu.edu | 1 |
| 301 | 109 | 02/26/99 | 03/02/99 | Kallemeyn, Pieter Cangahuala, Alberto Ely, Todd; Bell, David Guinn, Joseph Bar-Sever, Yoaz E. Lichten, Stephen Wu, Sien-Chong Levene, Erik; Vyas, Hemali | Constellation Design for a Mars-Orbiting Satellite Communication and Navigation Network | Jet Propulsion Lab, Voice: 818-354-9166, Fax: 818-393-6388, Pieter.H.Kallemeyn-Jr@jpl.nasa.gov | 1 |
| 302 | 49 | 02/15/99 |  | Willcockson, William H. | Mars Polar Lander Entry Descent & Landing Design | Lockheed Martin Astronautics, S8800, POB 179, Denver, CO 80201, Voice: 303-977-5094, Fax: 303-977-9345, william.h.willcockson@lmco.com | 1 |
| 303 | 111 | 02/26/99 | 03/02/99 | Johnston, M.D. Esposito, P.B. Alwar, V.; Demcak, S.W. Graat, E.J.; Burkhart, P.D. Portock, B.M. | The Strategy for the Second Phase of Aerobraking Mars Global Surveyor | Jet Propulsion Lab, California Institute of Technology, 4800 Oak Grove Dr, M/S 264-235, Pasadena, CA 91109, Voice: 818-393-1290, Fax: 818-393-3147, Martin.D.Johnston@jpl.nasa.gov | 1 |
| 304 | 118 | 03/01/99 | 03/02/99 | Guo, Yanping | Aladdin's Phasing and Mission Orbit Design | The Johns Hopkins Univ, APL, Rm 4-141, 11100 Johns Hopkins Rd, Laurel, MD 20723-6099, Voice: 240-228-7541/443-778-7541, Fax: 240-228-1093/443-778-1093, yanping_guo@jhuapl.edu | 1 |
| 305 | 112 | 02/26/99 | 03/02/99 | Lee, Wayne J. D'Amario, Louis A. Roncoli, Ralph B. Smith, John C. | Mission Design Overview for Mars 2003/2005 Sample Return Mission | Jet Propulsion Lab, California Institute of Technology, MS 264-380, 4800 Oak Grove Dr, Pasadena, CA 91109, Voice: 818-354-8784, Fax: 818-393-2902, wayne@cranberry.jpl.nasa.gov | 1 |
| 306 | 129 | 03/01/99 | 03/03/99 | D'Amario, Louis A. Bollman, Willard E. Lee, Wayne J. Roncoli, Ralph B. Smith, John C. | Mars Orbit Rendevous Strategy for the Mars 2003/2005 Sample Return Mission | Jet Propulsion Lab, California Institute of Technology, 4800 Oak Grove Dr, MS 301-276, Pasadena, CA 91109, Voice: 818-354-3209, Fax: 818-393-5214, louis.damario@jpl.nasa.gov, Willard.E.Bollman@jpl.nasa.gov, Wayne.J.Lee@jpl.nasa.gov, Ralph.B.Roncoli@jpl.nasa.gov, John.C.Smith-Jr@jpl.nasa.gov | 1 |

ATTACHMENT 5

20 March 1997

To:  	Session Chairs for the AAS/AIAA Astrodynamics Conference

Sun Valley, Idaho

From:  Technical Chairs,

Felix Hoots, AAS

Bernard Kaufman, AIAA

We want to thank you for volunteering to act as a session chair for the summer conference.  The dates of the conference are August 4-7, 1997 and the location is the Elkhorn Resort and Golf Club in Sun Valley, Idaho.  A tentative session title and schedule is listed below and is subject to change based on your evaluation of the abstracts in your session.  You may choose a more appropriate title for your session if you desire.

Enclosed you will find the abstracts that we have tentatively assigned to your session.  The address and other available information for the contact author (indicated by **) is also listed.

We are striving to improve the quality of the conference and are therefore asking that you review these abstracts for content, interest, originality, and above all quality.  If you feel that a paper does not meet standards please inform us that the paper should be rejected.  If a paper should be in another session tell us that also.  Also, consider the possibility of combining like papers by the same author if this is appropriate.  Otherwise, arrange the papers in the order that you feel appropriate with the intent of having 6 to 7 papers per session with a total of 25 minutes for each paper including 5 minutes for questions.  If a paper is a good one, it is acceptable to have 8 papers in a session – but no more than that.

Please return the enclosed sheet with the indicated information to us by March 31, 1997.   Faxing of the information will be good enough.  We will inform the authors as to acceptance or rejection of the papers.

Additionally, you will be asked to ensure that the authors in your session meet all deadlines for the abstract for publication and to see to it that they bring the required number of papers with them to the conference.  You should maintain contact with the authors periodically to see that they are on schedule.

Once again, thank you for your help and we look forward to a good conference this August.

AAS Technical Chair			AIAA Technical Chair

Felix Hoots					Bernard Kaufman

GRC International				Naval Research Laboratory

985 Space Center Drive, Suite 310		Code 8103

Colorado Springs, CO 80915			Washington, DC 20375

719/596-5395    719/596-6139 FAX		202/767-0513    202/404-7516 FAX

email: fhoots@grci.com			email: kaufman@ssdd.nrl.navy.mil

## ATTACHMENT 6

April 26, 1999

Dear Author:

We are pleased to inform you that your paper has been accepted for presentation at the AAS/AIAA Astrodynamics Specialist Conference in Girdwood, Alaska to be held August 16-19, 1999.  Please note the following:

- Please see the AAS website ( www.space-flight.org ) and check for the Girdwood conference to obtain complete author information including a preliminary program. Your assigned paper number will be listed in the preliminary program along with the name of your Session Chair. A set of instructions for the paper format, proceeedings submission/publication instructions, and a blank cover sheet will be available on the website May 1, 1999. Consider the site your primary source for author information.

- Each presenter will be scheduled for a total of 20 minutes (nominally a 15 minute presentation and 5 minute discussion).  Please keep in mind that the time schedule is fixed so that attendees may move between sessions.

- You must bring 50 copies of your paper with you to the meeting.  Additionally, you must bring an original copy that will be used for the proceedings.  These preprints will be for sale in the paper room at the meeting.  In addition, a proceedings will be published after the meeting.  It is important that you bring these copies with you as there is a “No paper-No podium” rule that will be strictly followed.

- Please note that publication in the proceedings is not considered an archival publication.  You are encouraged to submit your paper after the conference to one of the relevant journals such as:

Journal of the Astronautical Sciences

Kathleen Howell, Editor-in-Chief

School of Aeronautics and Astronautics

1282 Grisson Hall

Purdue University

West Lafayette, IN 47907

(765)494-5786;  (765)494-0307 FAX

howell@ecn.purdue.edu

Journal of Guidance, Control and Dynamics

George Schmidt, Editor-in-Chief

Mail Stop 57

The Charles Stark Draper Laboratory

555 Technology Square

Cambridge, MA 02139-3563

(617)258-3841; (617)258-2333

gschmidt@draper.com

- You must send  a 50 - 100 word abstract of your paper to both of the conference technical chairmen no later than 1 June.  This will be published in the conference program and will help attendees ascertain their interest in attending your presentation.  This should be sent by email as embedded text or as a WORD format attachment.  We will acknowledge our receipt of the abstract.  As with the requirement for the paper, this abstract is a necessity.

- Finally, please send a biographical sketch to the Session Chair no later than 1 July for use in making introductions.  There will be a Speaker’s Breakfast each morning of the conference for all speakers presenting on that day.  It is requested that you attend this breakfast so that you can meet you Session Chair and coordinate any final presentation details.

We thank you for submitting this paper for consideration at the meeting, for your work involved in preparing the paper, presenting it, and sending the final version for the proceedings.  We look forward to your participation in the Astrodynamics Conference.

AAS Technical Chair

Kathleen Howell

School of Aeronautics and Astronautics

GRIS 1282

Purdue University

West Lafayette, IN 47907

765/494-5786  765/494-0307

email:howell@ecn.purdue.edu

AIAA Technical Chair

Felix Hoots

GRC International

Suite 310

985 Space Center Drive

Colorado Springs, CO 80915

719/596-5395  719/596-6139

email: fhoots@grci.com

ATTACHMENT 7

April 3, 1997

Dear Author:

Your paper has been considered for presentation at the AAS/AIAA Astrodynamics Conference in Sun Valley, Idaho to be held August 4-7, 1997.  However, it has been determined that your paper is not appropriate for presentation at this conference for the following reason:

- ______  The subject matter is not consistent with the conference content.  We encourage you to consider submission to a more appropriate conference.

- ______  The content of your paper does not add significant new findings to the field of astrodynamics.  You may want to consider submitting it as an Engineering Note to an appropriate journal.

- ______  You have submitted a substantially similar version of your paper for another conference which will be held prior to this conference.  The call for papers clearly stated that only papers which have not been published or presented elsewhere would be considered.

- ______  You have previously submitted papers to our conference and have demonstrated a lack of common courtesy by failing to appear at the conference and giving us either no or very late notification of your withdrawal.

We thank you for submitting this paper for consideration at the meeting and for your interest in the conference..  We hope that you will consider our conference for presentation of your work in the future.

AAS Technical Chair			AIAA Technical Chair

Felix Hoots					Bernard Kaufman

GRC International				Naval Research Laboratory

985 Space Center Drive, Suite 310		Code 8103

Colorado Springs, CO 80915			Washington, DC 20375

719/596-5395    719/596-6139 FAX		202/767-0513    202/404-7516 FAX

email: fhoots@grci.com			email: kaufman@ssdd.nrl.navy.mil

ATTACHMENT 8

|  | 1999 ASTRODYNAMICS CONFERENCE |  |
| --- | --- | --- |
|  | Alyeska, Alaska |  |
|  | Aug. 15-18, 1999 |  |
| SCHEDULE DATE | EVENT | RESPONSIBILITY |
| March, 1998 | site selection | AAS GC&TC |
|  | Chairmen | GC: AAS Kaufman |
|  |  | AIAA Alfriend |
|  |  | TC:AAS Howell |
|  |  | AIAA Hoots |
| Mar-98 | AIAA TC approval form | GC |
| May-98 | draft call for papers | TC |
| Jun-98 | finalize call for papers | TC |
| Jun-98 | finalize hotel contract | GC |
|  | request reservation forms |  |
|  | for 2nd mailing in May 1998 |  |
| 10-Sep-98 | call for papers to AIAA-to appear in Nov. issue | TC |
|  | to AAS newsletter to appear in ****** issue |  |
| Oct-98 | selection of banquet | GC |
| Nov-98 | initial budget preparation for Feb meeting | GC/TC |
| Nov-98 | prepare material for first mailing | GC/TC |
| 3-Dec-98 | first general mailing | GC |
| Jan-99 | prepare final budget | GC/TC |
| Feb-99 | presentation to committees | GC |
|  | request session chairmen | TC |
| 15-Feb-99 | Abstracts due | TC |
| 1-Mar-99 | tentative session schedule | TC |
| 1-Mar-99 | final date for decision to hotel on need for 4th day | GC/TC |
| 1-Mar-99 | Probable extension of abstract deadline | TC |
| 11-Mar-99 | selection of session chairman | TC |
| 11-Mar-99 | abstracts to session chairman | TC |
| 11-Mar-99 | arrangements with Jacobs for title page and | GC |
|  | author instructions |  |
| 25-Mar-99 | review by session chair for accept/rejection | TC |
| 5-Apr-99 | final program | TC |
| 10-Apr-91 | acceptance letters/author instr./abstract form | TC |
|  | and hotel info |  |
| 10-Apr-99 | rejection letters | TC |
| 10-Apr-99 | cocktail party/cookout menu/final hotel details | GC |
| 19-Apr-99 | arrangements for abstract booklet | TC |
| 1-May-99 | final budget | GC |
| 13-May-99 | 2nd mailing to short list/reserv card/regist fee | GC |
| 13-May-99 | abstract due to TC | TC |
| 20-May-99 | abstracts to printer | TC |
| 3-Jun-99 | program summary to authors/final reminders | TC/session chairmen |
| 10-Jun-99 | final coordination /hotel | GC |
|  | tax exmpt status/billing procedures |  |
|  | cocktail party |  |
|  | Cookout |  |
|  | speakers breakfast |  |
|  | committee lunches |  |
|  | visual equipment/microphones |  |
|  | check on reservation status |  |
| 8-Jul-99 | arrangements with local bank | GC |
|  | check hotel reservation status |  |
| July **, 1999 | deadline for hotel |  |

ATTACHMENT 9

Some authors, especially from foreign countries, may require a letter of invitation rather than our normal acceptance letter.  Additionally, they may request more information for visa applications or may request financial assistance.  The following example may meet their needs.

# June 8, 1999

## Ms. Qun Fang

College of Astronautics

Northwestern Polytechnical University

Xi(an 710072

P.R. China

Dear Ms. Fang:

On behalf of the program committee for the AAS/AIAA Astrodynamics Specialist Conference we are pleased to inform you that your paper, entitled Design and Analysis of Space Station Based Micro-Satellite Networks, has been accepted for presentation in the following session,

### Session 2:	Formation Flying/Constellations

### Day/Date:	Monday AM; August 16, 1999

### Your paper has been assigned reference number AAS 99-313.  The reference number should be shown on correspondence and documents related to your paper.  Please be sure that your co-authors are informed of the acceptance of the paper.

### This letter serves as the official invitation on behalf of the AAS and AIAA for yourself and co-authors to attend the 1999 Astrodynamics Specialist Conference in Girdwood, Alaska, U.S.A., August 16-19, 1999.  (Spouses are also welcome.)  It is not a commitment on the part of AAS or AIAA to provide any financial support.

Enclosed is a list of instructions for authors.  Please follow them carefully to insure that your paper meets the guidelines for papers to be presented at the conference.  Please note that you are encouraged to complete your travel arrangements soon.  If you or your co-authors are unable to present the paper, please inform us as soon as possible.

We look forward to receiving your paper and its presentation at the conference.

Sincerely,

## Kathleen C. Howell	Felix Hoots

### AAS Technical Chair	AIAA Technical Chair

## School of Aeronautics and Astronautics	GRC International

GRIS 1282	Suite 310

Purdue University	985 Space Center Drive

West Lafayette, IN 47907	Colorado Springs, CO 80915

765/494-5786   765/494-0307	719/596-5395   719/596-6139

email:  howell@ecn.purdue.edu	email:  fhoots@grci.com

ATTACHMENT 10

##### Paper AAS 99-xxx

Insert Paper Title Here

Insert Author Names Here

Insert Author Organization Here

AAS/AIAA Astrodynamics

Specialist Conference

# Girdwood, Alaska		16-19 August 1999

AAS Publications Office, P.O. Box 28130, San Diego, CA  92129

ATTACHMENT 11

AAS/AIAA Astrodynamics SpecialistConference

### Session 1, 8:30 – 11:30 AM		Session Title:		Mission Design: Mars

#### Session Chair:	Robert G. Melton

  - Architectural Design for a Mars Communications & Navigation Orbital

Infrastructure

0830am	R.J. Cesarone, R.C. Hastrup, D.J. Bell, D.T.Lyons, K.G. Nelson

  - Mars Network Constellation Design Drivers and Strategies: A Navigation Perspective

0850am	P. Kallemeyn, T. Ely, J. Guinn, M. Jah, Y. E. Bar-Sever, S. Lichten, S-C. Wu, L. Romans, D. Bell, E. Levene

  - Mars Polar Lander Entry Descent & Landing Design

0910am	W. H. Willcockson

  - The Strategy for the Second Phase of Aerobraking Mars Global Surveyor

0930am	M.D. Johnston, P.B. Esposito, V. Alwar, S.W. Demcak, E.J. Graat, P.D. Burkhart, B.M. Portock

  - Aladdin's Phasing and Mission Orbit Design

1010am	Y. Guo

  - Mission Design Overview for the 2003/2005 Mars Sample Return Mission

1030am	L. A. D'Amario, R. B. Roncoli, J. C. Smith

  - Mars Orbit Rendevous Strategy for the Mars 2003/2005 Sample Return Mission

1050am	L. A. D'Amario, W. E. Bollman, W. J. Lee, R. B. Roncoli, J. C. Smith

  - Terminal Rendezvous Analysis and Design for the Mars Sample Return Mission

1110am	P. S. Kachmar, C. N. D'Souza, T. J. Brand

ATTACHMENT 12

Dear Session Chairs,

We are looking forward to seeing everyone at the AAS/AIAA Astrodynamics Specialist Conference in Girdwood, Alaska, August 16-19, 1999.

This is just a reminder to contact all the authors in your session and remind them of the following:

- The authors are reminded that all paper instructions are on the AAS web site. A new cover page is also on the site with the new AAS logo.

- The authors must bring 50 copies of their paper to the meeting.  Additionally, they must bring an original camera ready copy that will be used for the proceedings.

- The final version of the program is now available on the AAS web site. This version includes  paper numbers and session assignments as well as short abstracts for the papers as well as the conference schedule and activities.

- This is the last chance for authors to inform us if they require a 35 mm slide projector or VCR for their presentation. It will not be possible to accommodate last minute requests.

- The authors should provide a short biography to their session chairs.

It is extremely important that you provide this information to your session authors.  We will not be sending this message to them separately.   Forwarding this information is your responsibility as the session chair.  If you have any other questions or concerns, please let us know.

AAS Technical Chair

Kathleen Howell

School of Aeronautics and Astronautics

GRIS 1282

Purdue University

West Lafayette, IN 47907

765/494-5786  765/494-0307

email:howell@ecn.purdue.edu

AIAA Technical Chair

Felix Hoots

GRC International

Suite 310

985 Space Center Drive

Colorado Springs, CO 80915

719/596-5395  719/596-6139

email: fhoots@grci.com

ATTACHMENT 13

# Instructions for the Use of the Personal AAS/AIAA Conference Planner

For the Conference Chairmen:

- The planner lists typical events at an AAS sponsored conference.  This includes speaker’s briefings, coffee breaks, technical committee meetings and receptions.  It is intended to allow a conference attendee to organize which papers and events he/she plans on attending.

- For each day, the following columns are provided:

  - Time of Day -- To be filled in by the conference chairmen.  Note, in some past conferences, papers have been scheduled simultaneously with committee meetings.

  - A personal use column with a ‘√’ at the top.  The column should be reserved for personal use.  The conference attendee can use this column to indicate if they attended the paper, or if they purchased the paper, or for any other use.

  - Session ID -- To be left blank.

  - Room -- To be filled in by the conference chairmen for known events, otherwise to be left blank.  The sample sheet has room names filled in for some of the events from the January 2000 AAS/AIAA Space Flight Mechanics Meeting in Clearwater, FL.  These, obviously, will have to be changed.

Activity/Paper – Known activities should be filled in by the conference chairmen but should not span the entire column, so as to allow the user to write in their personal plans.  (For example, not everyone attends the technical committee meeting.)  The remaining rows should be left blank for personal use.